## Gap Analysis - Example
NTPC Gap Analysis Summary | Project: Capital Projects Stage Gating Process - Best Practice Research Gaps |  |  |  | Date: August 28, 2018
Objective / Best Practice / Opportunity | Source | Current State | Gap or Deficiency | Actions | Status | Comments | Theme/ Category
Try to state what the opportunity is here as it fits to the Gap/Deficiency. It also helps to help explain what benefits this opportunity will provide to the process! | Where was this gap identified? Was it during the Current State exercise? Was it during the Best Practice or Voice of Customer? During Future State exercise? | What is currently happening in the process? | What is the gap/deficiency? This is stating the problem in the process. Try to stay away from what the opportunity is and more specific to the issue. | What are the steps, known as of right now, that would need to be taken to implement the opportunity(ies)? | Is this Opportunity "In Scope" or "Out of Scope" of the project? Those that are "In Scope" will be expected to be actioned on and will be paired with an Implementation Plan. | Any other helpful information can go here! | Use broader categories to help place opportunities together. It is quite possible that many opportunities are related and may even be remedied together!
There is an opportunity to implement a gate that determines if projects will be accepted (i.e. Project Acceptance Gate). Ensure valid projects are on the final list and helps priority and reduces the amount of invalid projects. Also support planning as it provides more criteria when evaluating the project (i.e scope and solution etc.) | Best Practice Research - Sask Power | Projects are identified and initiated by Asset Management and Operations based on current need and the 20 year plan. | There is little justification or determining factors to proceed with planning and Initiation of projects which end up on the 1 year Capital Plan List. This causes rework of the 1 year Capital Plan List, and the potential to execute inappropriate projects which strains resources and budgets. | A gate or tool and associated criteria is required to determine if projects should proceed to planning. This is regardless of budget. Resources to be involved in this evaluation or scoring need to be determined. | In Scope |  | Gate - Project Identification
Project's costs estimation are used as part of the gate structure - This will allow for each gate to have criteria about how well known the costs have to be at each gate. Cost control. | Best Practice Research - Sask Power | Project Briefs are signed off using an AFE Matrix. | There are no formalized controls to ensure that |  | In Scope | estimatation tightens up through each gate | Gate Criteria - Cost Estimation Criteria (At Each Gate)
5 gates identified | Best Practice Research - Sask Power | NTPC needs gates | how many gates is the right size | PROJECT INITIATION (PHASE) PROJECT ACCEPTANCE (GATE) PROJECT DEFINITION PROJECT READINESS (GATE) DESIGN AND PROCURE CONSTRUCTION READINESS (GATE) CONSTRUCTION ENERGIZATION READINESS (GATE) PROJECT CLOSURE PROJECT CLOSURE (FINISH GATE) | In Scope |  | Gate - 5 have been Selected
checklists were created as part of the workflow to prompt discussion of gate advancement | Best Practice Research - Sask Power | do we have any? | would this be something NTPC would value? | multiple documents | In Scope |  | Gate Criteria - Checklists
Implement the following stage gate points: JUSTIFY PROJECT PLAN PROJECT ACTIVATE PROJECT CONTROL PROJECT END PROJECT | Best Practice Research - PMI | Currently there are no formal stage gates. | There are no standardized formal stage gates within the organization. These gates could be standardized with other leaders in project management. | Investigate if these stage gates will fit the organization | In Scope | this language does deviate from the book a bit | Gate - 5 have been Selected
Implement the following stage gate points: PROJECT INITIATION PROJECT PLANNING PROJECT EXECUTION PROJECT MONITORING AND CONTROLING PROJECT CLOSURE | Best Practice Research - Nalcor | Currently there are no formal stage gates. | There are no standardized formal stage gates within the organization. This gates could be standardized with other leaders in project management. | Investigate if this stage gates will fit the organization | In Scope |  | Gate - 5 have been Selected
Implement the following stage gate points: identify select define execute commission | Best Practice Research - Husky | Currently there are no formal stage gates. | There are no standardized formal stage gates within the organization. This gates could be standardized with other leaders in project management. | Investigate if this stage gates will fit the organization | In Scope |  | Gate - 5 have been Selected
Implement a form which allows for the PM group to see the justification of a project. This will be needed to ensure each project has support and justification. | Project Identification (Initiation Gate) - Best Practice Research - Sask Power | Currently project briefs are the only measure for justification for a project and it is more of a questionnaire that may not suit all the questions of AME (PM group) | Project briefs are the only measure for justification for a project and it is more of a questionnaire that may not suit all the questions of AME (PM group) | Develop a form or a list of required questions or checklist items which need to be checked off prior to a project to beginning! Can we utilize CMMS to capture capital project work? Does it have the information or does it need to be tailored? Will this still be needed if there is an Asset Management Priority tool being used? What about revamped Project Briefs? | In Scope |  | Gate Criteria - Job Justification for Project Identification
There is an opportunity to use the new Asset Management Project Initiation framework as a key input the Initiation/Identify Gate for approval towards next Phase in Project Management. This will ensure the NTPC is not performing rework and using support of current process and tools and support for these. | AME - Asset Management | Currently there is an asset management tool that is being tested for project identification. | The majority of projects do not go through an asset management tool to investigate if they meet a criteria to be moved through the Project Management lifecycle | Can we utilize the Asset Management identification tool for all projects? And be the main criteria for the Iniation Stage Gate… Is this tool too heavy? Too light? How do we enforce this tool on each project? | In Scope |  | Gate Criteria - Asset Prioritization tool in the Project Identification Phase
There is an opportunity to define what the governance structure is for each gate. Who or what wil ensure that projects cannot pass without scrutiny and which allows them to move from one phase to the next. This resource will need to have controls to ensure that projects flow through the gate properly at all times for consistency and ensure needs are met. | General discussion | Currently there are no gates to govern | Currently there are no gates to govern | Define the governance required for each gate. Define what will control the projects flowing throug the gates. | In Scope |  | Gates - All Gates
There is an opportunity to create an Identification Stage prior to an Iniation Phase. This phase is to ensure that projects have to pass a gate to get onto a list. | Best Practice Research - General | Currently there is not gate for identification | Currently there is not gaate for identification | Identify which tools will be used here and what inputs will be needed for this gate? Asset Mgt Framework? Project Brief? New Justification Form? | In Scope |  | Gate - Project Identification
There is an opportunity to ensure proper review is had by any role responsible in the process. This is to ensure scoping of project is correct and can move forward confidently. This can come in the form of Project Brief (review). | Best Practice Research - General | Currently governance is not standard within the process which is led by AME. | Currently governance is not standard within AME | Identify which resources in AME need to review the Project Brief and provide "sign off" Explore possibility to create and implement a RACI and checklist for peer review process. This includes; Project Brief review checklist and a potential to utilize a K2 form (etc.) | In Scope |  | Gate Criteria - Initiate Gate
There is an opportunity to quantify the acceptable variance levels to become more accurate with the actuals cost versus the initial budgeted. To ensure that the project can be evaluated at each gate using the criteria that has been developed (cost criteria). Example: Budget analysis from formal planning identifies large variances should go back through previous phase. | Best Practice Research - Columbia Power and Guide to Cost Predictability in Construction | Currently there are no identified criteria for brief cost evaluations | There is little evaluation being conducted for cost and confidence for advancement of the project. | Identify and review brief cost variances from current past(Last year) for amounts, reasons and flow of the document to completion. Develop criteria for evaluation. | In Scope |  | Gate Criteria - Budget Variance
There is an opportunity to develop a criteria to ensure scope of project remains consistent and/or captured and approved during Gate review. | Best Practice Research - General Discussion an Research | Currently there are no identified criteria for brief scope evaluations | There is little evaluation being conducted for scope and concept for advancement of the project which may lead to scope not matching initial scope. | Develop criteria for evaluation of scope when flowing through gate. This is to capture changes in scope and ensure original intent is met or if changes have occurred it is captured and approved. | In Scope |  | Gate Criteria - Scoping at All Gates
There is an opportunity to further the criteria for evaluation of a project at the planning phase to iclude PSRA as a formalized step. | Best Practice Research - General Discussion an Research | Currently there is no formalized PSRA step for review during the planning phase. | Without having PSRA as a formalized step a project can go through without the proper risk evaluation which puts safety of workers at risk. | Ensure PSRA step is a part of the mandatory checklist (or review requirement) during the planning phase gate to move into execution. | In Scope |  | Gate Criteria - Planning Phase
There is an opportunity to define what each gate means to the NTPC. Example: Husky Gate 1 ; do we have funding and do we understand what we are being asked to deliver? (Slide 21 of the Husky research document) | Best Practice Research - Husky | Currently do not have formal gates to define | Without having formalized definitions of what the gate is implemented for there is room for difference in understanding and intpretation. | Once gates have been developed and placed definitions of what those gates are for can be created. | In Scope |  | Gates - All Gates
Deficiencies need to be identified in execution phase and can be handled within execution phase There is an opportunity to have flexibility to avoid stalling project. | MARK (Reality) | Currently projects can be commissioned with unacceptable deficiencies | Sometimes projects can be commissioned without all unacceptable deficiencies addressed | Develop criteria in execution/closing stage gate addressing deficiencies with use of lists. Update the deficiencies list template to ensure the who and whens of a project are added. | In Scope |  | Gate Criteria - Execution & Closing Phases
There is an opportunity to formalize the inclusion of the project management close report and increase transparency Time/Actuals/Scope for project. | MARK and SARAH (Reality) | Currently there pm close report is not formally included (timely) | Project closures are delayed due to the PM close report not being done in a timely manner, this creates a backlog of project closures during the end of the fiscal year and this causes resource strain in Finance. | Formalize the Project Close PM form into the Closing Gate so that no project causes delay in the actual project closeout. | In Scope |  | Gate Criteria - Closing Phase
There is an opportunity to formally incorporate disposal requirements for assets during the Initiation stage gate within the Project Brief. There is an opportunity to formally incorporate disposal requirements for assets during the Planning stage gate within the project review. There is an opportunity to define governance surrounding asset disposals for projects. | Best Practice Research - General Discussion | Currently asset disposals are not formalized and no standard procedure exists surrounding execution and governance. | Without having a specific asset disposal plan in place projects may be completed without proper disposal evaluations and plans in place this leads to untimely and costly disposals. | Develop criteria for Initiation and Planning stage gates to include appropriate level of details for disposals. Ensure gate governance is appropriate to approve disposal plans. | In Scope |  | Gate Crieria - Initiation & Planning Phases
There is an opportunity to ensure that the Operations team is formally included in the decision process for project commisioning. | Best Practice Research - General Discussion | Currently Operations is not formally included in commision oversight. | Without having the appropriate Operations engagement with project commissioning there is risk for disconnection between PM team and Operations upon change-over of commissioned project. This leads to dissatisfied stakeholders and a risk that the project commission has unforeseen/not-approved deficiencies. | To identify what formal criteria is there to ensure the proper Operations team is involved for project commissioning and all other gates. | In Scope |  | Governance - All Gates
There is an opportunity to align contract closures with Contract and Procurement processes | Best Practice Research - General Discussion | Currently there is no alignment between C&P and PM closeouts | Without this alignment projects remain open and causes a backlog of projects to closeout or contratcs to be closed. | to identify criteria related to contract closures in the project closeout gate. | In Scope |  | Gate Criteria - Closing Phase
There is an opportunity to consider a project risk/complexity classification criteria (1-low, 2-med, 3-high) that corresponds to the level of governance and documentation. FYI Currently projects over 5MM have PUB review direction criteria required. | Best Practice Research - Husky | There is no risk/complexity classification currently | A lack of a classification results in every project receiving the same level of detail or rigor, which can bog down simple projects, or possibly be inusfficient for large/complex projects | Review previous year's projects and identify possible classification criteria. Develop goveranance structure and documentation requirements for different classifications of projects. Conduct test cases on completed projects to determine possible impact of classification system. Develop governance and criteria at new stage gates for different classifications of projects. | Out of Scope |  | Gate Criteria - Project Identification
There is an opportunity to clarify the demarkation points for project types and subsequent levels of details/governance. | Best Practice Research - General Discussion | There are only financial demarkation points existing. | Without having more clarified demarkation points a stage gating process might put additional constraints on some projects and not enough on others. | Consider stage gate light process for direct purchases and other potential jobs/candidates. | In Scope |  | Gate - Light and Heavy Versions?
There is an opportunity to adopt a well defined governance structure similar to Husky Example. PM, Sponsor, Engineer, Analyst, Operations, | Best Practice Research - Husky | There are no formalized governance roles and definitions for projects and at stage gates | Without proper governance and definitions of roles and responsibilities there is a risk that projects do not have the right roles/people involved. | Define potential governance roles at each stage gate. | In Scope |  | Governance - All Gates
There is an opportunity to implement a gate that determines if projects will be accepted (i.e. Project Acceptance Gate). Ensure valid projects are on the final list and helps priority and reduces the amount of invalid projects. Also support planning as it provides more criteria when evaluating the project (i.e scope and solution etc.) | Best Practice Research - Sask Power | Projects are identified and initiated by Asset Management and Operations based on current need and the 20 year plan. | There is little justification or determining factors to proceed with planning and Initiation of projects which end up on the 1 year Capital Plan List. This causes rework of the 1 year Capital Plan List, and the potential to execute inappropriate projects which strains resources and budgets. | A gate or tool and associated criteria is required to determine if projects should proceed to planning. This is regardless of budget. Resources to be involved in this evaluation or scoring need to be determined. | In Scope |  | Gate - project Identification
There is an opportunity to include groups such as Design or Operations earlier on in the Project Brief Process. This will ensure that the project has more expertise and input to create a better product. | Current State SIPOC Process Map - Initiate Phase | Project Briefs are signed off using an AFE Matrix. | While sign off is required to approve a Project Brief, there are times when not having a quality review from Design or Operations causes rework later on in the project, or possibly installation of sub-optimal infrastructure. Waiting for signatures can cause delays as well. | A standard checklist or gate is required where Project Briefs are circulated and must be reviewed before the project proceeds to Planning. The audience and authority to sign off, review, or approve needs to be determined and accounted for (Must have to proceed, nice to have) Potential for K2 Form to be utilized to manage circulation of Project Briefs and obtaining signatures. | In Scope |  | Project Brief
There is an opportunity to improve the quality of the document to focus as much on scope and schedule in addition to budget. This will ensure that there is more accurate and useful information to move forward in executing the project (i.e better scoping etc.) | Current State SIPOC Process Map - Initiate Phase | Project Briefs are completed with a focus on budget | The current briefs lack certain information on scope and schedule and are completed to varying degrees of quality (some are better than others). | Review the Project Brief process & ensure a standard, high quality, consistent document is produced. This includes the brief content to be revamped. Train/educate staff on writing effective briefs to eliminate re-writes and rework and get faster acceptance. Verify on who the owner is of the document during its lifecycle. | Out of Scope |  | Project Brief
There is an opportunity to allot an appropriate amount of time to complete Project Briefs. This will ensure the PB quality is superb! This will allow us to capitalize on resource availability. | Current State SIPOC Process Map - Initiate Phase | Project Briefs are completed under short timelines. | Under short timelines, the quality of the Project Brief suffers. This is caused by a number of issues, including the back and forth of agreeing on project identification with Operations, budget adjustments, or addition of new projects not on the 1 year list. | Set a reasonable cut-off for project identification to ensure Asset Management and Project Managers have enough time to prepare quality Project Briefs. Only Emergency projects will be pushed through after this cut-off, and projects that come up last minute because of Poor Planning will require special approval. If a defined cut-off for Briefs is set, this would limit the amount of re-work in the Capital Budget, and possibly make reporting to the Board of Directors simpler. Changes to finalizing the list earlier (September) may already be underway. | Out of Scope |  | Project Brief
There is an opportunity to requrie briefs for all Capital Projects regardless of Budget. This will ensure that each project is validated and has a basis. | Current State SIPOC Process Map - Initiate Phase | Project Briefs are not required for projects under $75,000 | For projects under $75,000 there is no accountability for these smaller projects. Questions like What are you doing, how much are you spending, why are you doing it should all still be asked and answered, and someone needs to be accountable for the project. | Project briefs will be required no matter what the value, but for projects under $75,000, no AFE signature is required. The brief will still be circulated to other groups for review. There may be a K2 form going in that might replace the need for a brief, or perhaps a "light" brief is required for projects under this threshold. | Out of Scope |  | Project Brief
There is an opportunity to refine the PM process using Market Pricing as part of initiating and planning large Design Build Projects. Allows for accurate project budgets. | Current State SIPOC Process Map - Initiate Phase | This has been done once and there is a plan to do this again. | There is no formal process on when to do this or not do this (cost threshold, scope, complexity, etc.). | Obtaining this market pricing will provide NTPC with the opportunity to be accurate on costing the project out. | Out of Scope |  | Market Pricing
There is an opportunity to finalize the Current Year Capital Plan in September. This will allow us to capitalize on resource availability. | Current State SIPOC Process Map - Initiate Phase | In the current year, the Captial Plan List was finalized in March | If the Capital Project List is finalized in March, this leave little time for planning and execution of projects. | Changes to finalizing the list earlier (September) may already be underway. This will help with board reporting and provide a window for project brief preparation | Out of Scope | Capital List - This one allows number 7 (Under short timelines, the quality of the Project Brief suffers. This is caused by a number of issues, including the back and forth of agreeing on project identification with Operations, budget adjustments, or addition of new projects not on the 1 year list.) to occur | Gate - Project Identification
There is an opportunity to finalize JCRs ahead of the March Board Meeting. This will ensure that there are no or minimal JCRs to complete post-board approval. Incentive for the PM to provide more accurate forecasts. | Current State SIPOC Process Map - Initiate Phase | In the current year, the JCR list was finalized after the March Board Meeting. | If the JCR list is finalized this late, this leaves little time for planning and execution of projects. | Changes to finalizing the JCR list earlier may already be underway. | Out of Scope |  | JCRs
There is an opportunity to change the timing of when the project list is relayed to Finance. This will help with setting up project numbers prior to the end of the fiscal year. This will help with board reporting and provide a window for project brief preparation | Current State SIPOC Process Map - Initiate Phase | Currently they get created just prior to the new fiscal year or in the new fiscal year. | Creating Project Numbers is a very cumbersome process. The list of projects which require numbers occurs late into year-end - this makes it difficult to setup Project Numbers as it contends with the Project Closure cycle. | Changes to finalizing the list earlier may already be underway. | In Scope (Probably) | Project List Timing | Gate - Project Identification
There is an opportunity to install a Project Initiation Stage Gate following the Project Brief Sign-Off and Project Manager Assignment . A stage gate will ensure that the defined criteria are in place before proceeding with a project to the Planning phase. Any project that does not meet the defined criteria will go through one of the selected pasths (stop, go, rework, etc.) - This provides a "go-no-go" at this point. | Current State SIPOC Process Map - Initiate Phase | Currently, there is no stage gate in the Initiation Phase | With no stage gate in place, there is no standard process or criteria to assess capability to complete the project, or ability to control projects that move forward without a proper brief, or assignment of a PM | Need to define Criteria for Stage Gate (Brief Signed, Project on the Capital List, Budget from Capital Plan and Project Brief Match or the difference is known and approved (by Sarah), Brief Reviewed by other areas) Need to define the Attendees/Governance/Decision Making Team | In Scope |  | Gate - project Initiation
There is an opportunity to collaborate more with the Design group. This will ensure there is a alignment b/w design and the plan and less rework. | Current State SIPOC Process Map - Planning Phase | Tasks are assigned, but collaboration is limited. | A lack of collaboration with the Design group leads to rework of design and a lack of alignment between the design and the project plan. | There are tasks underway to improve the levels of collaboration. | Out of Scope |  | Collaboration
There is an opportunity to consistently execute a Project Kickoff Formalizing the kickoff process would ensure consistent information dissemenation, on-boarding, introductions, alignment. It allows for questions and answers and teambuilding. | Current State SIPOC Process Map - Planning Phase | Kickoff meetings are conducted for complex projects. | Kickoff meetings are inconsistent in their occurrence (50% of the time) and the content (they are done differently by different resources). Some are email, in person, or phone. | Criteria for kickoff meetings is required, various templates might be required. ex. small projects require a phone meeting, large meetings require face to face, etc. | Out of Scope |  | Project Kickoff
There is an opportunity to require As Builts or update existing As Built. Less rework and reduce the amount of poor quality designs due to poor quality As-Builts. | Current State SIPOC Process Map - Planning Phase | There is no requirement to receive As Built Drawings | With no reliable As Builts, site visits are required for ever project. Sometimes Designs are completed based off of old versions of As Builts, reqiuring rework when a site visit results in identification of out of date As Builts. Confidence in As Builts is low and even good drawings are not relied on. | Initially, there needs to be a large effort to ensure all existing drawings are up to date, starting with identification of all known out-of-date drawings. When projects are initiated, all related drawings should be reviewed and updated to ensure all drawings on record in NTPC are current. Going forward, all construction projects will require As Built Drawings, which then need to be filed and made available throughout the organization. | Out of Scope |  | As Builts
There is an opportunity to improve the quality of Design Drawings (Preliminary, 25%, 95% Adding a quality control check will ensure appropriate drawings are produced, either a rational based inspection, 100% inspection, or spot inspections. (likely 100% is the best option) | Current State SIPOC Process Map - Planning Phase | There is no quality control check on drawings. | With no quality control check, poor quality designs are possible and there is a lack of consistency, requiring rework. This can also affect Field Work, as dimensions might be incorrect or unclear, and this increases cost and possibly affects safety. | Peer review (at 95%), field review (at 25% and 95%), and quality control review (95%) might be required. Ensure the authority for review and approval of drawings is determined (Might already be in the works). What requires sign off and what doesn't? PCAP | Out of Scope |  | Design Drawing Quality
There is an opportunity to align Operations Resources and the Project Manager around Resource Needs | Current State SIPOC Process Map - Planning Phase | There is some alignment currently when Individual Project Plans are being Developed. | There have been big strides here in recent years, but resourcing issues caused by a lack of alignment between Operations and Project Managers. Scheduling, getting dedicated staff, conflicting priorities are all examples of issues faced. | Formal sessions to review individual project plans between PMs and Operations will be required for all projects. Two way communication is required between Operations and PMs if events or situations arise that change project schedules. | Out of Scope |  | Alignment with Operations RE Resource Needs
There is an opportunity to formalize the Project Safety Risk Analysis (PSRA) timing at the end of the Planning Phase and possibly include it as a Planning Stage Gate Criteria | Current State SIPOC Process Map - Planning Phase | The PSRA timing is not formalized currently. | A lack of formalization means that there is potential for the project to be delayed. Safety and Operations require this document, so producing it late causes delays. | Formalize the timing of the PSRA to allow for review and approval. Require Signed PSRA as part of the Planning Stage Gate Criteria. | Out of Scope |  | PSRA Timing
There may be an opportunity to circulate the Approved Design to other groups. Ensures that there is an avenue for divisional review and comment. | Current State SIPOC Process Map - Planning Phase | Currently, Asset Managers and HSE do not receive copies of the Approved Design | Unsure as to the exact gap or deficiency that is caused, but this warrants a discussion with these and possibly other groups to determine if they need to receive the Approved Design. Safety Review is a requirement for the approval of the design, as is Operability. | Determine if the circulation of these drawings is appropriate, and at what stage these groups should be involved in the review and approval. | Out of Scope |  | Drawing Circulation/Peer Review
There is an opportunity to install a Project Planning Stage Gate following the Finalization of the Project Management Plan . This ensures there is a "go-no-go". | Current State SIPOC Process Map - Planning Phase | Currently, there is no stage gate in the Planning Phase | With no stage gate in place, there is no standard process or criteria to assess is the project should move forward past Planning. Projects that have budget increases or scope changes may not be assessed appropriately before continuing currently. | A stage gate will ensure that the defined criteria are in place before proceeding with a project to the Execution phase. Any project that does not meet the defined criteria will go through one of the selected pasths (stop, go, rework, etc.) Need to define Criteria for Stage Gate (PSRA Approved, PMP Approved, Design Approved, Budget Approved) Need to define the Attendees/Governance/Decision Making Team | In Scope |  | Gate - Project Planning
There is an opportunity to put a standard pre-inspection of materials/equipment process in place. This will ensure that correct material is on site for the work to be completed and quality of material/equipment is sufficient. | Current State SIPOC Process Map - Execution Phase | Currently, inspection of materials is not a standard process | With no standard pre-inspection of materials, there are opportunities that incorrect, missing, or unsuitable materials will be shipped to site. This causes rework, delays, and additional shipping costs. | Implement a standard pre-inspection process for materials at the source (Pre-shipping), and when they arrive on site (order checking). This lives with Logistics (internally). | Out of Scope |  | Materials/Equipment Pre-Inspection
There is an opportunity to communicate with site personnel that on-site project work is occurring. This will allow all staff and site persons to know of the work being conducted. | Current State SIPOC Process Map - Execution Phase | Currently, there is no formal communication with on-site personnel regarding on-site work. | While it is likely that on certain sites, word of mouth travels, or senior staff pass word along that work will be conducted, but with no formalized process, there is a possibility that some staff might not know about upcoming work. This might cause conflicts or frustration with staff whose regular work may be disrupted, or surprise if on-site staff is expected to prepare or participate in the work. | Implement a standard communication for projects to inform on-site staff of any and all upcoming work. Consider an annual calendar once project schedules have been determined, followed by individual communication prior to all project work commencing. | Out of Scope |  | Communication with On Site Personnel
There is an opportunity to improve work quality through a Quality Assurance/Quality Control Program | Current State SIPOC Process Map - Execution Phase | Currently, there is no Quality Assurance/Quality Control Program | There are no QA/QC programs (formalized) on work, there is the potential for quality levels to suffer, resulting in more breakdowns, deficiencies, or outages. | Implement a QA/QC process for work based on a to be determined criteria (Type of work, complexity of job, budget, location, Contractor, etc.). Determine if 100% of projects require this check, or if spot checks or other rational strategy. | Out of Scope |  | QA/QC Program
There is an opportunity to install a Project Execution Stage Gate following the Testing, Commissioning, and Deficiency Identification. This will ensure that every project can enter the closing process effectively. | Current State SIPOC Process Map - Execution Phase | Currently, there is no stage gate in the Execution Phase | With no stage gate in place, there is no standard process or criteria to assess is the project should move forward past Execution. NTPC may accept work or release holdbacks prematurely and without the proper checks in place. Need a gate to have criteria to allow the project or infrastructure to go into service following commissioning. This criteria will include must haves, nice to haves, and do not needs. Clearly indicate around the deficiencies list what is outstanding and needs to be done, and what is acceptable to address moving forward. Anything that limits the infrastructure from going into service must be addressed before moving to the next phase. | A stage gate will ensure that the defined criteria are in place before proceeding with a project to the Monitoring phase. Any project that does not meet the defined criteria will go through one of the selected paths (stop, go, rework, etc.) Need to define Criteria for Stage Gate (Deficiencies Resolved, Testing Successful, Commissioning Complete, etc.) Need to define the Attendees/Governance/Decision Making Team | In Scope | Need to place this as a concurrent process underlining the other processes (Solve and CI Team) - The start of the Closing phase (commissioning) will be the gate to end execution. | Gate - Project Execution
There is an opportunity to improve consistency of Monthly Status Update Reports. This will ensure that the Monthly Financial Report is accurate to the actual project information. | Current State SIPOC Process Map - Monitoring Phase | Currently the Monthly Status Update Report produces inaccurate information due to inconsistent user inputs. | There are inconsistencies with the Monthly Status Update Reports resulting in inaccurate information which feeds into the Monthly Financial Report | A K2 Form has been formalized and communicated to all users for quality inputs. Training and direction to be communicated to all users who provide inputs. | Out of Scope |  | Monthly Status Update Reports
There is an opportunity to install a Project Monitoring Stage Gate following the Completion of Audits | Current State SIPOC Process Map - Monitoring Phase | Currently, there is no stage gate in the Monitoring Phase | With no stage gate in place, there is no standard process or criteria to assess is the project should move forward past design. Projects that have budget increases or scope changes may not be assessed appropriately before continuing currently. | A stage gate will ensure that the defined criteria are in place before proceeding with a project to the Closing phase. Any project that does not meet the defined criteria will go through one of the selected paths (stop, go, rework, etc.) Need to define Criteria for Stage Gate (Audit Passed, Concerns Addressed, Budget Met, etc.) Need to define the Attendees/Governance/Decision Making Team | In Scope | Audits are when the monitoring is "complete" | Gate - Monitoring will be throughout the process
There is an opportunity to formalize the Operations Acceptance process. This will ensure that acceptance of the executed work will be more effective. | Current State SIPOC Process Map - Closing Phase | Currently, the Operations Acceptance process is not formalized | The current process is inconsistently executed, which opens up the possibility for Operations to inappropriately accept infrastructure, or have infrtastrucutre turned over to them without a formal acceptance. | Create formal process for Operations Acceptance or approval to be put into service. Possibly create checklist or formal criteria, or build on the Monitoring Gate to determine if Operations accepts infrastructure | In Scope | Will be partially addressed by Execution Stage Gate. Will need to create criteria in order to ensure that the inputs to the stage gate for Execution is effective (prior to CI project closing). | Gate Criteria - Closeout
There is an opportunity to improve the Maintenance Training process | Current State SIPOC Process Map - Closing Phase | Currently, there is Maintenance Training | WHAT IS WRONG WITH MAINTENANCE TRAINING | HOW DO WE FIX IT? | Out of Scope | Refer to above (The current process is inconsistently executed, which opens up the possibility for Operations to inappropriately accept infrastructure, or have infrtastrucutre turned over to them without a formal acceptance.) | Maintenance Training
There is an opportunity to formalize the PM Closing Report as a requirement into the Closing stage gate | Current State SIPOC Process Map - Closing Phase | Currently, the Project Management Close Report is not always completed and especially not consistently completed for all projects during the same step of the process. | The current reality is that the PM Closing Report may never occur because there are no formal checks to force it to happen. | Investigate the possibility of introducing this opportunity as the Closing stage gate criteria. | In Scope |  | Gate Criteria - Closeout
There is an opportunity to streamline the HSE Environmental Reports for disposals (ATA). This ensures that disposals on projects are accurate. | Current State SIPOC Process Map - Closing Phase | Currently, the ATA process is ineffective and inefficient | The ATA generated does not produce accurate information and is reviewed inappropriately | Utilize a K2 form to formalize this process | Out of Scope |  | HSE Reports
There is an opportunity to formalize an "internal warranty" with Operations | Current State SIPOC Process Map - Closing Phase | Currently, there is no standardized or consistent method to identify deficiencies | Unidentified deficiencies post-commission acceptance result in less reliable infrasture, more issues, rework. | Investigate if an "Internal Warranty" will benefit both AME and Operations so that defficiencies which occur passed Execution stage gate are resolved. | Out of Scope |  | Internal Warranty
There is an opportunity to improve the usage of project coding by implementing controls | Current State SIPOC Process Map - Closing Phase | Currently, project coding is not consistently used | Improper use of coding results in complexity, poor reporting, and the wasted time requried to fix issues. | Error proofing or training to ensure people use the right codes. PM is notified when a resource requests for timesheet coding access | Out of Scope |  | Project Coding
There is an opportunity to ensure all contracts are closed. This will help eliminate rework. | Current State SIPOC Process Map - Closing Phase | Currently, the contract closing process is inconsistent | The triggers to close contracts are inconsistent, resulting in contracts being open past the project finish date. Contracts Manager must call around several times a year to check on open contracts, which is a waste of time and resources. | Investigate the Contracts and Procurement CI Project for overlap Investigate if this opportunity can sit under Closing stage gate | In Scope | Review Contracts and Procurement CI project for overlap | Gate Criteria - Closeout
There is an opporunity to increase visibility of scope, time, and budget on financial closeout and sign-off | Current State SIPOC Process Map - Closing Phase | Currently the visibility for the financial closeout of a project is unable to portray and confirm the work which has been executed. | Closeout report does not provide informative details on the actual work executed. | Investigate to see if documentation (executive summary) is possible to be created and provided for project closeout (and if this works) | Out of Scope |  | Gate Criteria - Closeout
There is an opportunity to install a Project Closing Stage Gate following the Projcet Management, Financial, and Contract Closings. A stage gate will ensure that the defined criteria are in place before formally closing out the project. Any project that does not meet the defined criteria will go through one of the selected paths (Close or rework, etc.) | Current State SIPOC Process Map - Closing Phase | Currently, there is no stage gate in the Closing Phase | With no stage gate in place, there is no standard process or criteria to assess if the project should be closed off. Projects that do not formally close remain open in the financial system and clutter up lists and systems. Interest costs remain on the open job. | Need to define Criteria for Stage Gate (PM Close Report Complete, Financial Project Closeout Complete, Contract Close Complete) Need to define the Attendees/Governance/Decision Making Team | In Scope | Need to define governance for each stage gate! | Governance - All Gates
There is an opportunity to formalize a justification form and questionnaire for project initiation stage | General Discussion | Currently, there is no justification form. | With no justification projects, all projects are moved forward with little to no rationale. While a majority of projects are good intentioned, a lack of justification can result in pet projects, or projects being initiated that do not meet strategic goals or the mission/vision of NTPC. | Develop project justification form for use prior to the project management process commencing, or at the very least very early on in the process. Implement Form and determine criteria or governance for go-no go of projects that are justified (or not) | In Scope |  | Gate - project Identification
There is an opportunity to implement AACE guidelines for planning and costing on projects over a certain estimated cost $$$ | General Discussion | Currently AACE is not used | Without a standard guideline to follow projects can pass through project management without formal scrutiny | Research what AACE standards would be and for what cost. Where can thise be implemented and at what Stage Gate? | Parking Lot

## Gap Analysis
NTPC Gap Analysis Summary | Project Title: |  |  |  | Date: August 28, 2018
Objective / Best Practice / Opportunity | Source | Current State | Gap or Deficiency | Actions | Status | Comments | Theme/ Category
Try to state what the opportunity is here as it fits to the Gap/Deficiency. It also helps to help explain what benefits this opportunity will provide to the process! | Where was this gap identified? Was it during the Current State exercise? Was it during the Best Practice or Voice of Customer? During Future State exercise? | What is currently happening in the process? | What is the gap/deficiency? This is stating the problem in the process. Try to stay away from what the opportunity is and more specific to the issue. | What are the steps, known as of right now, that would need to be taken to implement the opportunity(ies)? | Is this Opportunity "In Scope" or "Out of Scope" of the project? Those that are "In Scope" will be expected to be actioned on and will be paired with an Implementation Plan. | Any other helpful information can go here! | Use broader categories to help place opportunities together. It is quite possible that many opportunities are related and may even be remedied together!