## 1 - Governance - Imp Plan
Opportunity | Define the governance required for each gate. Define what will control the projects flowing through the gates.
Goal(s) / Objective(s) | Confirmed gates and checklists implemented
Sponsor: Scott Spencer | Strategic Owner: Scott Spencer | Coordinator: Mark Horton | Resources Required: Mark Horton Annetter Rupert Paul Grant
Actions/Milestones | Responsible | Timeline | Progress Reviews:
Contact Paul about Integrating Corporate Governance | Mark | 2019-01-30 | Coordinator: Weekly Strategic/Sponsor: Bi-Monthly | When we were generating these solutions, we simply wanted to identify who would be responsible for completing and checking gate criteria. We had the indivduals identified, so this solution as it intended might be complete. How exactly does integrating corproate governance into the stage gates work?
Integrate Corporate Governance into Gate Checklists | Mark/CI | N/A
Update Flow Charts or Diagrams to incorporate changes | Mark/CI | N/A
Communicate Checklists to all Involved (Identify audience, determine method of communication, communicate, follow up questions, etc.) | CI To Delegate | 2019-02-06
Key Measures of Success: | Checklists implemented for 100% of Capital Projects

## 2- Deficiencies - Imp Plan (hidden)
Opportunity | Develop criteria in execution/closing stage gate addressing deficiencies with use of lists. Update the deficiencies list template to ensure the who and whens of a project are added.
Goal(s) / Objective(s) | Confirmed gates and checklists implemented
Sponsor: Scott Spencer | Strategic Owner: Scott Spencer | Coordinator: Mark Horton | Resources Required: Mark Horton Annette Rupert Paul Grant
Actions/Milestones | Responsible | Timeline | Progress Reviews:
Key Measures of Success: | Checklists implemented for 100% of Capital Projects

## 3 - Closing - Imp Plan
Opportunity | Formalize the Project Close PM form into the Closing Gate so that no project causes delay in the actual project closeout. Post-Construction report to provided with Financial Close for clarity and to minimize delays in closing.
Goal(s) / Objective(s) | Process in place to ensure Finance receives closeout report with post construction report at same time so the project can be properly closed out in the GP.
Sponsor: Scott Spencer | Strategic Owner: Scott Spencer | Coordinator: Mark Horton | Resources Required: Mark Horton Annette Rupert Paul Grant Sarah Froese Jamie Hunt
Actions/Milestones | Responsible | Timeline | Progress Reviews:
Communicate to resources to expect the change (Identify audience, determine method of communication, communicate, follow up questions, etc.) | Mark | 2019-01-30 | Coordinator: Monthly Strategic/Sponsor: Upon implementation
Develop Training/Notification for checkilist review for PMs | Mark/Brad? | 2019-01-30
Key Measures of Success: | Post Construction Report to be sent to Finance with Closeout Report on 100% of Capital Projects

## Imp Plan - EXAMPLE
NOTE: Every Opportunity (Gap) on the Gap Analysis will require an Implementation Plan. Some opportunities can be bunched together on the same Implementation Plan BUT one still should be used. Implementation Plans are used so that the Project Lead can push the opportunities found into the process. Without one, it makes it difficult to track the progress and creates risk for the opportunity to never be implemented correctly. Having an opportunity not be implemented correctly could lead to; (1) the process to be analyzed again (rework), (2) change resistance and (3) partial implementation which may affect the process negatively.
Implementation Plan EXAMPLE
Opportunity (Pulled from the Gap Analysis) | Can we utilize the Asset Management priortization tool for all projects? And be the main criteria for the Initiation Stage Gate… Is this tool too heavy? Too light? How do we enforce this tool on each project?
Goal(s) / Objective(s) | Determine if a standardized tool can be applied to all projects regardless of size or complexity.
Sponsor: Scott Spencer | Strategic Owner (SLT): Scott Spencer | Coordinator (Typicall the Project Lead): Mark Horton | Resources Required: Mark Horton Annetter Rupert Paul Grant
Actions/Milestones (What tasks need to be done?) | Responsible (Who is doing the task?) | Timeline (When will this task be completed?) | Progress Reviews: (Who and how often will someone review this implementation plan to make sure it keeps being actioned?)
Review Current Tool & Recent Uses to determine how well it works currently | Annette | 2019-01-15 | Coordinator (Mark Horton): Bi-Weekly
Discuss Revisions to Tool based on any required improvements | Annette | 2019-01-30
Conduct Test Cases for recent projects based on size/complexity/budget. | Mark | 2019-02-15
Identify Gaps in tool based on project size/complexity/budget | Mark/Annette | 2019-02-28
If Required, Create & Implement Slim/Light Version of Tool for use in Small/lower complexity/low budget projects | Mark | 2019-03-15
Communicate changes to appropriate resources (Identify audience, determine method of communication, communicate, follow up questions, etc.) | Mark/Scott | 2019-03-31
Key Measures of Success: (When all of these tasks are complete, what demonstrates that the work completed has been successful? Try to use %,$$$,Hours or some othe quantative measure. Example: 100% of the new process will be documented and communicated out to resources | 5 Test Cases Complete & Satisfactory (If Required) Life Version of Tool Created to 100%

## Implementation Plan
Opportunity
Goal(s) / Objective(s)
Sponsor: | Strategic Owner: | Coordinator: | Resources Required:
Actions/Milestones | Responsible | Timeline | Progress Reviews:
Key Measures of Success: