## Notes&Instructions
Notes and Instructions: 1. The "Project Classification Determination" is used to determine the classification level that will be assigned to a project (Small Project, Level 1 to Level 5). 2. There is some subjectivity in determining the individual ratings and this can affect the classification process and the deliverables required for a project. To minimize the chance of erroneous results it is expected that a reviewer and an approver must agree with the results and their agreement will be noted by their signatures in the "Approvals" section of the form. 3. Enter the assigned points between a range of 0 -10 in the "Project Category Evaluation Matrix" section (in light blue) for each project category (refer to the "Recommended Scoring for Points Range" section for a guideline to scoring in the six project categories). 4. The weighting factor is based on the following breakdown for a project: Time 10%, Cost 30%, Complexity 30%, Risk 30% for a total of 100% for the project. 5. The total calculated weighted points will be applied as per the breakdown in the "Project Classification" section and the final level will be shown in the dark blue cell to the right of the "Project Classification Level" label. 6. Assigning points for each category must be based with the following considerations:
Notes and Instructions:
1. The "Project Classification Determination" is used to determine the classification level that will be assigned to a project (Small Project, Level 1 to Level 5).
2. There is some subjectivity in determining the individual ratings and this can affect the classification process and the deliverables required for
a project. To minimize the chance of erroneous results it is expected that a reviewer and an approver must agree with the results and their
agreement will be noted by their signatures in the "Approvals" section of the form.
3. Enter the assigned points between a range of 0 -10 in the "Project Category Evaluation Matrix" section (in light blue) for each project category
(refer to the "Recommended Scoring for Points Range" section for a guideline to scoring in the six project categories).
4. The weighting factor is based on the following breakdown for a project: Time 10%, Cost 30%, Complexity 30%, Risk 30% for a total of 100% for the project.
5. The total calculated weighted points will be applied as per the breakdown in the "Project Classification" section and the final level will be shown
in the gray cell to the right of the "Project Classification Level" label.
6. Assigning points for each category must be based with the following considerations:
TIME
The timing of the project must be based on the total project life cycle from cradle to grave.
COST
The cost must be based on a Class 5 Order of Magnitude Estimate for the total installed cost.
COMPLEXITY
The complexity of the project requires some subjectivity when determining points. The following may be used as a guideline to support/justify the weighing which drives the level of complexity
| Number of stakeholders Number of operations (lines of communication) | Level of impact on Operations Environmental Assessment required | Level of regulatory complexity Contracting strategy Impact on communities (Duty to Consult) | Organizational Matrix Number of Tie-Ins to existing facilities
| Simple Complexity (Points = 1) - Like in kind replacement - Single Discipline Scope - Single workface - Scope clearly defined with realistic timelines | Low to Moderate Complexity (Points = 2-3) - 2 or 3 disciplines - Solution readily available using well understood technologies - Process complexity is low - Scope clearly defined with realistic timelines | Moderate to High Complexity (Points = 4-5) - Multiple tie-ins to existing facilities - Shut downs may be required - Multi-discipline scope - Single or multiple workfaces | High Complexity (Points = 6-8) - Project executed by >10 people - Schedule is aggressive, fixed and cannot be changed - Disruption to daily operations - Challenging communications and coordination effort - Multiple contractors, multiple workfaces with increased coordination effort - Complex procurement and contracting strategy - Solution is difficult to achieve or technology is proven but new to business unit | Extreme Complexity (Points = 9-10) - Installing into existing facility - Multi-discipline scope and multiple workfaces with significant integration - Solution involves complex technologies - Multiple (staged) tie-ins - Shut down activities required - Multiple stakeholders with communications and coordination effort - Complex procurement items - Complex procurement and contracting strategy - Significant impact to operations - Project objectives dependent on external factors
RISK
The project risk requires some subjectivity when determining points. First identify the risks at a macro level (overall project) in terms of likelihood and measures of success. Secondly, additional assessment may include the following to support / justify the scoring:
| Schedule Cost Technology NPV Sensitivity | Regulatory Interdependencies Safety, Health, Environment Production Significance | Investment Security Legal
For example,
if the residual risk is ≤12, then the macro level risk may be considered as Insignificant and be scored at 0-1
if the residual risk is ≤20, then the macro level risk may be considered as Minor and be scored at 2-3
if the residual risk is ≤30, then the macro level risk may be considered as Moderate risk and be scored at 4-5
if the residual risk is ≤40, then the macro level risk may be considered as Major and be scored at 6-8
if the residual risk is ≥40, then the macro level risk may be considered as Catastrophic risk and be scored at 9-10
FORM
UNCONTROLLED DOCUMENT WHEN PRINTED

## Project Evaluation Matrix
Project Classification Form Document # CP-FRM-PM-02 rev 0
Project Classification Determination
Site:
Project Name: |  |  |  | Date Issued:
Project No: |  |  |  | Revision No:
Project Manager |  |  |  | Revision Date:
Project Sponsor:
APPROVALS
Role | Name & Title |  |  | Signature |  | Date
Project Manager:
Program Manager:
Manager, Portfolio Planning & Controls:
Approver:
Approver:
CALCULATED PROJECT CLASSIFICATION |  |  |  | OFFICIAL PROJECT CLASSIFICATION Note 1
Project Category Evaluation Matrix
|  |  | Points Range | Assigned Points | Weighting Factor | Weighted Points
Project Category |  | Time | 0 - 10 |  | 1 | 0
|  | Cost | 0 - 10 |  | 3 | 0
|  | Complexity | 0 - 10 |  | 3 | 0
|  | Risk | 0 - 10 |  | 3 | 0
Total |  |  | 0 - 10 | 0 | 10 | 0
Recommended Scoring for Points Range (see instructions below)
|  | Points Range | Time | Cost | Complexity | Risk
|  | 1 | < 3 Months | < $0.1 M | Simple Complexity | Insignificant
|  | 2 - 3 | 3 Months - 1 Year | $0.1 M - $0.5 M | Low to Moderate Complexity | Minor
|  | 4 - 5 | 1 - 2 Years | $0.5 M - $2 M | Moderate to High Complexity | Moderate
|  | 6 - 8 | 2 - 3 Years | $2 M - $5 M | High Complexity | Major
|  | 9 - 10 | > 3 Years | > $5 M | Extreme Complexity | Catastrophic
Project Classification
Category Classification |  | SMALL PROJECT / LEVEL 1 | LEVEL 2 | LEVEL 3 | LEVEL 4 | LEVEL 5
Range of Total Weighted Points (Calculated from Evaluation Matrix Above) |  | 0 - 30 | 21 - 40 | 41 - 60 | 61 - 80 | 81 - 100
Note 1: If there is a variance between the calculated Classification Level and Classification Level of which the project will be executed as, then an explanation of the variance must be included in the Project Charter.
COST
30%
PROJECT
ORG STRUCTURE
5%
RISK
20%
COMPLEXITY
20%
CONTRACT TYPE
5%
TIME
20%

## Project Classification
Title: Project Classification
Document # CP-FRM-PM-02 rev 0
|  |  | Project Classification (Complexity) |  |  |  |  | Min Project Specific Requirements
Stage |  | SMALL PROJECT | LEVEL 1 | LEVEL 2 | LEVEL 3 | LEVEL 4 | LEVEL 5 | Project Definition | TIC Cost Evaluation
CONCEPT STAGE | [7 empty] | (typical <1%) | Order of Magnitude AACE Class 5+ (> +100% / -50%)
SCOPING STUDY STAGE | [7 empty] | (typical:1%-5%) | AACE Class 5 (+100% / -50%)
PRE-FEASIBILITY STUDY STAGE | [7 empty] | (typical 2% /Option (5-15%)) | AACE Class 4 (+50% / -30%)
FEASIBILITY STUDY STAGE | [7 empty] | (typical15%-80%) | AACE Class 3 (30% / -20%)
IMPLEMENTATION & CLOSEOUT STAGE | DETAILED DESIGN | [6 empty] | (typical 80-100% (Field Assistance)) | AACE Class 2 (+20% / -15%)
| PROCUREMENT | [6 empty] | 100% (Field Assistance) | n/a
| CONSTRUCTION | [6 empty] | (Field Assistance) | n/a
| COMMISSIONING | [6 empty] | (Field Assistance) | n/a
| CLOSEOUT | [6 empty] | 100% As-Builts | n/a
AFE
AFE
Stage Gate
Detailed Engineering
Construction
Commissioning
CLOSE OUT
AFE
Stage Gate
Stage Gate
Stage Gate
Stage Gate
Stage Gate
Stage Gate
AFE
Detailed Engineering
Construction
Commissioning
CLOSE OUT
AFE
Detailed Engineering
Construction
Commissioning
AFE
Detailed Engineering
Construction
Commissioning
AFE
Detailed Engineering
Procuring Goods and Service
Construction
Commissioning
CONCEPT
CLOSE OUT
CLOSE OUT
CLOSE OUT
AFE
AFE
AFE
CONCEPT
CONCEPT
CONCEPT
CONCEPT
Stage Gate
AFE
AFE
AFE
AFE
Basic Options Assessment
Develop Options - Final Option
Propose Options
Propose Options
Stage Gate
Stage Gate
PRE-FEASIBILITY DESIGN
Develop Options - Final Option
Develop Options - Final Option
Basic Engineering on Final Option
Basic Engineering on Final Option
Basic Engineering on Final Option
Basic Engineering on Final Option
Procuring Goods and Service
Procuring Goods and Service
Procuring Goods and Service
Procuring Goods and Service
CONCEPT
AFE
Procuring Goods and Service
Construction
CLOSE OUT
Basic Options Assessment
Detailed Engineering
Commissioning
Optional Stage Gate
Optional Stage Gate
Optional Stage Gate
Optional Stage Gate
Optional Stage Gate

## Small Project Deliverables
| Small Projects - Project Deliverables |  |  |  | Document: Document # CP-FRM-PM-02 rev 0
Project Stages
| Initiate and Plan Phase | Execute, Monitor / Control and Closure Phase
|  |  | Minimum Deliverables | Deviations | Comments
1 | ü |  | Project Charter including Business Justification, Scope of Work and Execution Plan
2 | ü |  | Capital Cost Estimate
3 | ü |  | Project Schedule
4 | ü |  | Project Risk Identification |  | Risks must be identified and documented
5 | ü |  | AFE Package Submission & Approval
6 |  | ü | Progress and Performance Reports to Sponsor, Stakeholders, Process Owner, etc |  | The frequency of reporting determined and agreed upon at the start of the project. Reporting will be generally narrative.
7 |  | ü | Project Change Control
8 |  | ü | Turnover Requirements |  | Only required for projects with construction activities
9 |  | ü | Final Acceptance by Operations |  | Only required for projects with construction activities
10 |  | ü | AFE Closure Form
The above noted minimal deliverables required for each stage must be used as guidance. The project manager in conjunction with the manager, portfolio planning & control must assess the level of effort required and include additional requirements based on the needs of the project. This will serve as the basis of all project planning activities.

## Level 1 Deliverables
| Level 1 Projects - Project Deliverables |  |  |  | Document: Document # CP-FRM-PM-02 rev 0
Project Stages
| Concept | Implementation & Closeout
|  |  | Typical Deliverables | Deviations | Comments
1 | ü |  | Project Charter including Business Justification, Scope of Work and Execution Plan
2 | ü |  | Class 3 Capital Cost Estimate for Implementation
3 | ü |  | Level 3 Schedule for Implementation
4 | ü |  | AFE Package Submission & Approval
5 | ü |  | Work Breakdown Structure
6 |  | ü | Project Risk Assessment |  | Updated and managed throughout project
7 |  | ü | Org Chart, Roles & Responsibilities
8 |  | ü | Regulatory Approvals
9 |  | ü | Monthly Progress and Performance Reports to Sponsor, Stakeholders, Process Owner & Portfolio |  | The frequency of reporting determined and agreed upon at the start of the project and must include compliance to SH&E reporting requirements. Reporting will be generally narrative.
10 |  | ü | Stage Gate Scorecard |  | Mandatory if Detailed Design gate is required
12 |  | ü | Project Design Basis, Design Criteria, Area Criteria |  | Project Design Basis - draft developed in Concept for AFE prep
13 |  | ü | Constructability Review
14 |  | ü | Process Flow Diagrams, General Arrangements, Single Line Diagrams, Piping and Instrumentation Diagrams
15 |  | ü | Construction Execution Plan
16 |  | ü | Contract Scope (Schedules A&B)
17 |  | ü | IFC Drawings
18 |  | ü | CWP Issue for Construction
19 |  | ü | CWP Risk Assessment
20 |  | ü | FIWP Framework and Execution
21 |  | ü | As-Builts
22 |  | ü | Turnover Package
23 |  | ü | Final Acceptance (Certificate of Operational Readiness and Certificate of Final Acceptance and Turnover)
24 |  | ü | Commissioning Report (when required)
25 |  | ü | AFE Closure Form
26 |  | ü | Project Closure and Turnover Matrix
27 |  | ü | Lessons Learned
28 |  | ü | Master Data Set-Up
The above noted minimal deliverables required for each stage must be used as guidance. The project manager in conjunction with the manager, portfolio planning & control must assess the level of effort required and indicate any deviations in the appropriate column. This will serve as the basis of all project planning activities. Additional deliverables may be included based on the needs of the project.

## Level 2 Deliverables
| Level 2 Projects - Project Deliverables |  |  |  |  | Document: Document # CP-FRM-PM-02 rev 0
Project Stages
| Concept | Feasibility | Implementation & Closeout
|  |  |  | Typical Deliverables | Deviations | Comments
1 | ü | ü |  | Project Charter including Business Justification, Scope of Work and Execution Plan
2 | ü | ü |  | Capital Cost Estimate for Next Stage and Estimate for Implementation
3 | ü | ü |  | Resource Loaded Schedule for Next Stage and high-level schedule for Implementation
4 | ü | ü |  | AFE Package Submission & Approval
5 | ü | ü |  | Work Breakdown Structure
6 |  | ü |  | Project Risk Assessment |  | Updated and managed throughout project
7 |  | ü |  | Life Cycle Value Assessment (LCVA) |  | Optional LCVA conducted in Feasibility
8 |  | ü | ü | Org Chart, Roles & Responsibilities
9 |  | ü | ü | Equipment/Material Specification
10 |  | ü | ü | Regulatory Approvals
11 |  | ü |  | Project Design Basis, Design Criteria, Area Criteria
12 |  | ü |  | Basic Design (15-40%)
13 |  | ü |  | Process Flow Diagrams, General Arrangements, Single Line Diagrams, Piping and Instrumentation Diagrams
14 |  | ü |  | Studies Report
15 |  | ü | ü | Constructability Reviews
16 |  | ü | ü | Progress and Performance Reports to Sponsor, Stakeholders, Process Owner & Portfolio |  | The frequency of reporting determined and agreed upon at the start of the project and must include compliance to SH&E reporting requirements. Reporting will be generally narrative.
18 |  |  | ü | Project Execution Plan and associated management plans (when warranted)
19 |  |  | ü | Final Design (40-100%)
20 |  |  | ü | Contract Scope (Schedules A&B)
21 |  |  | ü | CWP Issue for Construction
22 |  |  | ü | CWP Risk Assessment
23 |  |  | ü | FIWP Framework and Execution
24 | ü | ü |  | Stage Gate Scorecard
25 |  |  | ü | As-Builts
26 |  |  | ü | Final Acceptance (Operational Readiness and Final Acceptance and Turnover)
27 |  |  | ü | Commissioning Report (when required)
28 |  |  | ü | AFE Closure Form
29 |  |  | ü | Project Closure and Turnover Matrix
30 |  | ü | ü | Lessons Learned
31 |  |  | ü | Master Data Set-Up
The above noted minimal deliverables required for each stage must be used as guidance. The project manager in conjunction with the manager, portfolio planning & controls must assess the level of effort required and indicate any deviations in the appropriate column. This will serve as the basis of all project planning activities. Additional deliverables may be included based on the needs of the project.

## Level 3 Deliverables
| Level 3 Projects - Project Deliverables | [5 empty] | Document: Document # CP-FRM-PM-02 rev 0
Project Stages
| Concept | Pre-Feasibility | Feasibility | Implementation & Closeout
[5 empty] | Minimum Deliverables | Deviations | Comments
1 | ü | ü | ü |  | Project Charter including Business Justification, Scope of Work and Execution Plans
2 | ü | ü | ü |  | Capital Cost Estimate for Next Stage and Estimate for Implementation
3 | ü | ü | ü |  | Resource Loaded Schedule for Next Stage and high-level schedule for Implementation
4 | ü | ü | ü |  | AFE Package Submission & Approval
5 | ü | ü | ü |  | Work Breakdown Structure
6 |  | ü |  |  | Project Risk Assessment |  | Updated and managed throughout project
7 |  | ü |  |  | Environmental Assessment Determination
8 |  | ü |  |  | Life Cycle Value Assessment (LCVA)
9 |  | ü | ü |  | Org Chart, Roles & Responsibilities
10 |  | ü | ü |  | Communication Matrix
11 |  |  | ü | ü | Equipment/Material Specification
12 |  |  | ü |  | Regulatory Approvals
13 |  | ü | ü |  | Project Design Basis, Design Criteria, Area Criteria
14 |  | ü |  |  | Preliminary Design (1-15%)
15 |  | ü |  |  | Final Option Recommendation
16 |  |  | ü |  | Basic Design (15-40%)
17 |  | ü | ü |  | Studies Report
18 |  |  | ü |  | Process Flow Diagrams, General Arrangements, Single Line Diagrams, Piping and Instrumentation Diagrams |  | Preliminary PFDs, GAs, etc. developed in Pre-Feasibility
19 |  |  | ü | ü | Constructability Reviews
20 |  | ü | ü | ü | Progress and Performance Reports to Sponsor, Stakeholders, Process Owner & Portfolio |  | The frequency of reporting determined and agreed upon at the start of the project and must include compliance to SH&E reporting requirements.
22 |  |  |  | ü | Project Execution Plan and Associated management plans (when warranted)
23 |  |  |  | ü | Final Design (40-100%)
24 |  |  |  | ü | Contract Scope (Schedules A&B)
25 |  |  |  | ü | Construction Management Plan
26 |  |  |  | ü | CWP Issue for Construction
27 |  |  |  | ü | CWP Risk Assessment
28 |  |  |  | ü | FIWP Framework and Execution
29 |  |  |  | ü | As-Builts
30 | ü | ü | ü |  | Stage Gate Scorecard
31 |  |  |  | ü | Commissioning Management Plan
32 |  |  |  | ü | As-Builts
33 |  |  |  | ü | Final Acceptance (Operational Readiness and Final Acceptance and Turnover)
34 |  |  |  | ü | Commissioning Report (when required)
35 |  |  |  | ü | AFE Closure Form
36 |  |  |  | ü | Project Closure and Turnover Matrix
37 |  | ü | ü | ü | Lessons Learned
38 |  |  |  | ü | Master Data Set-Up
The above noted minimal deliverables required for each stage must be used as guidance. The project manager in conjunction with the manager, portfolio planning & controls must assess the level of effort required and indicate any deviations in the appropriate column. This will serve as the basis of all project planning activities. Additional deliverables may be included based on the needs of the project.

## Level 4 Deliverables
| Level 4 Projects - Project Deliverables | [6 empty] | Document: Document # CP-FRM-PM-02 rev 0
Project Stages
| Concept | Scoping | Pre-Feasibility | Feasibility | Implementation & Closeout
[6 empty] | Minimum Deliverables | Deviations | Comments
1 | ü | ü | ü | ü |  | Project Charter including Business Justification, Scope of Work and Execution Plans
2 | ü | ü | ü | ü |  | Capital Cost Estimate for Next Stage and Estimate for Implementation
3 | ü | ü | ü | ü |  | Resource Loaded Schedule for Next Stage and high-level schedule for Implementation
4 | ü | ü | ü | ü |  | AFE Package Submission & Approval
5 | ü | ü | ü | ü |  | Work Breakdown Structure
6 |  | ü |  |  |  | Project Risk Assessment |  | Updated and managed throughout project
7 |  | ü | ü | ü |  | Studies Report
8 |  |  | ü |  |  | Environmental Assessment Determination
9 |  |  | ü |  |  | Life Cycle Value Assessment (LCVA) |  | Optional LCVA conducted in Scoping
10 | ü | ü | ü | ü |  | Org Chart, Roles & Responsibilities
11 | ü | ü | ü | ü |  | Communication Matrix
12 |  |  |  | ü | ü | Equipment/Material Specification
13 |  |  |  | ü | ü | Regulatory Approvals
14 | ü | ü | ü | ü |  | Project Design Basis, Design Criteria, Area Criteria
15 |  |  | ü |  |  | Preliminary Design (1-15%)
16 |  |  | ü |  |  | Final Option Recommendation
17 |  |  |  | ü |  | Basic Design (15-40%)
18 |  |  |  | ü |  | Process Flow Diagrams, General Arrangements, Single Line Diagrams, Piping and Instrumentation Diagrams |  | Preliminary PFDs, GAs, etc. developed in Pre-Feasibility
19 |  |  |  | ü | ü | Constructability Reviews
20 |  | ü | ü | ü | ü | Progress and Performance Reports to Sponsor, Stakeholders, Process Owner & Portfolio |  | The frequency of reporting determined and agreed upon at the start of the project and must include compliance to HS&E reporting requirements.
22 |  |  |  |  | ü | Project Execution Plan and associated management plans (when warrented)
23 |  |  |  |  | ü | Final Design (40-100%)
24 |  |  |  |  | ü | Contract Scope (Schedules A&B)
25 |  |  |  |  | ü | CWP Issue for Construction
26 |  |  |  |  | ü | CWP Risk Assessment
27 |  |  |  |  | ü | Construction Management Plan
28 |  |  |  |  | ü | FIWP Framework and Execution
29 | ü | ü | ü | ü |  | Stage Gate Scorecard
30 |  |  |  |  | ü | Commissioning Management Plan
31 |  |  |  |  | ü | Commissioning Report
33 |  |  |  |  | ü | As-Builts
34 |  |  |  |  | ü | Turnover Package
35 |  |  |  |  | ü | Final Acceptance (Operational Readiness and Final Acceptance and Turnover)
36 |  |  |  |  | ü | Commissioning Report (when required)
37 |  |  |  |  | ü | AFE for Closure Form
38 |  |  |  |  | ü | Project Closure and Turnover Matrix
39 | ü | ü | ü | ü | ü | Lessons Learned
40 |  |  |  |  | ü | Master Data Set-Up
The above noted minimal deliverables required for each stage must be used as guidance. The project manager in conjunction with the manager, portfolio planning & controls must assess the level of effort required and indicate any deviations in the appropriate column. This will serve as the basis of all project planning activities. Additional deliverables may be included based on the needs of the project.

## Level 5 Deliverables
| Level 5 Projects - Project Deliverables | [6 empty] | Document: Document # CP-FRM-PM-02 rev 0
Project Stages
| Concept | Scoping | Pre-Feasibility | Feasibility | Implementation & Closeout
[6 empty] | Minimum Deliverables | Deviations | Comments
1 | ü | ü | ü | ü |  | Project Charter including Business Justification, Scope of Work and Execution Plans
2 | ü | ü | ü | ü |  | Capital Cost Estimate for Next Stage and Estimate for Implementation
3 | ü | ü | ü | ü |  | Resource Loaded Schedule for Next Stage and high-level schedule for Implementation
4 | ü | ü | ü | ü |  | AFE Package Submission & Approval
5 | ü | ü | ü | ü |  | Work Breakdown Structure
6 |  | ü |  |  |  | Project Risk Assessment |  | Updated and managed throughout project
7 |  | ü | ü | ü |  | Studies Report
8 |  |  | ü |  |  | Environmental Assessment Determination
9 |  |  | ü |  |  | Life Cycle Value Assessment (LCVA) |  | Optional LCVA conducted in Scoping
10 | ü | ü | ü | ü |  | Org Chart, Roles & Responsibilities
11 | ü | ü | ü | ü |  | Communication Matrix
12 |  |  |  | ü | ü | Equipment/Material Specification
13 |  |  |  | ü | ü | Regulatory Approvals
14 | ü | ü | ü | ü |  | Project Design Basis, Design Criteria, Area Criteria
15 |  |  | ü |  |  | Preliminary Design (1-15%)
16 |  |  | ü |  |  | Final Option Recommendation
17 |  |  |  | ü |  | Basic Design (15-40%)
18 |  |  |  | ü |  | Process Flow Diagrams, General Arrangements, Single Line Diagrams, Piping and Instrumentation Diagrams |  | Preliminary PFDs, GAs, etc. developed in Pre-Feasibility
19 |  |  |  | ü | ü | Constructability Reviews
20 |  | ü | ü | ü | ü | Progress and Performance Reports to Sponsor, Stakeholders, Process Owner & Portfolio |  | The frequency of reporting determined and agreed upon at the start of the project and must include compliance to SH&E reporting requirements.
22 |  |  |  |  | ü | Project Execution Plan and associated management plans (when warranted)
23 |  |  |  |  | ü | Final Design (40-100%)
24 |  |  |  |  | ü | Contract Scope (Schedules A&B)
25 |  |  |  |  | ü | CWP Issue for Construction
26 |  |  |  |  | ü | CWP Risk Assessment
27 |  |  |  |  | ü | Construction Management Plan
28 |  |  |  |  | ü | FIWP Framework and Execution
29 | ü | ü | ü | ü |  | Stage Gate Scorecard
30 |  |  |  |  | ü | Commissioning Management Plan
31 |  |  |  |  | ü | Commissioning Report
33 |  |  |  |  | ü | As-Builts
34 |  |  |  |  | ü | Turnover Package
35 |  |  |  |  | ü | Final Acceptance (Operational Readiness and Final Acceptance and Turnover)
36 |  |  |  |  | ü | Commissioning Report (when required)
37 |  |  |  |  | ü | AFE Closure Form
38 |  |  |  |  | ü | Project Closure and Turnover Matrix
39 | ü | ü | ü | ü | ü | Lessons Learned
40 |  |  |  |  | ü | Master Data Set-Up
The above noted minimal deliverables required for each stage must be used as guidance. The project manager in conjunction with the manager, portfolio planning & controls must assess the level of effort required and indicate any deviations in the appropriate column. This will serve as the basis of all project planning activities. Additional deliverables may be included based on the needs of the project.